## Executive Summary
Metric | Value | Notes / Owner
Total Tasks | 27 | Across Infra, DaaS, ITTE
% Completed | 18% | Majority in Planning phase
High-Impact Risks | 5 | EDP flow, cross-subscription, no POC, tool selection
Key Dependencies | 4 | Deloitte inputs, NSG approval, Infra provisioning
Target Go-Live | 2025-11-25 | Tentative cutover
Overall Health | At Risk (Yellow) | First-time PROD execution

## Master Tracker
# | Category | Service / Platform | Task Description | Sub-Details / Deliverables | Responsible Team(s) | Owner / POC | Status | Comments / Dependencies | Target Date | Completion Date | Risk Level | Dependency | Remarks / Mitigation Plan | Planned Effort (hrs) | Actual Effort (hrs)
1 | Infra | Azure SQL DB | PID creation | PID created for new environment | Infra – Masood | Masood | ✅ Done | Initial setup completed | 2025-11-01 | 2025-11-01 | Low |  |  | 2 | 2
2 | Infra | Azure SQL DB | New subscription access check | Verify access & additional permissions | Infra – Masood | Masood | 🔄 In Progress | Awaiting cloud governance approval | 2025-11-08 |  | Medium |  | Follow up with governance | 4
3 | Infra | Azure SQL DB | CPOP setup | Create CPOP under new sub; link DaaS/Masood/ARE | Infra / DaaS / ARE |  | 🟡 Planned |  | 2025-11-10 |  | Medium | PID completion |  | 3
4 | Infra | Azure SQL DB | BOM setup | Review and update bill of materials | DaaS / ARE |  | 🟢 Not Started |  | 2025-11-10 |  | Low |  |  | 2
5 | Infra | Azure SQL DB | Network security/firewall | Update NSG and whitelist IPs | ARE |  | 🟡 Planned | Coordinate with security ops | 2025-11-12 |  | Medium | Infra provisioning |  | 5
6 | Infra | Azure SQL DB | Azure services provisioning | Create resources (VMs, storage, SQL, etc.) | ARE |  | 🟡 Planned | Depends on PID and NSG completion | 2025-11-15 |  | High | NSG setup |  | 10
7 | Infra | Azure SQL DB | Bitbucket repo setup | New repo for EDP YAML and code | ARE |  | 🔄 In Progress | Repo URL shared | 2025-11-07 |  | Low |  |  | 4
8 | Infra | Azure SQL DB | EDP YAML configuration | Configure YAML for new subscription | ARE |  | 🟢 Not Started | Sync with DaaS | 2025-11-12 |  | Low | Repo setup |  | 3
9 | Infra | Azure SQL DB | Environment shake-down | Validate infra post-setup | ARE |  | 🟢 Not Started | Run health checks | 2025-11-18 |  | Medium | Infra provisioning |  | 4
10 | DaaS | Azure SQL DB | Current DB sizing inventory | Size, object count, list of schemas/tables/views | DBA / ARE / DaaS |  | ✅ Done | Sizing report shared | 2025-11-03 | 2025-11-03 | Low |  |  | 6 | 6
11 | DaaS | Azure SQL DB | Bitbucket access check | Confirm write/merge access to repo | DaaS |  | 🔄 In Progress | Access pending for few users | 2025-11-09 |  | Medium |  | Follow up with Infra | 2
12 | DaaS | Azure SQL DB | Backup & restore (point-in-time) | Execute EDP flow to restore backup | ARE / DaaS |  | 🟡 Planned | Requires maintenance window | 2025-11-12 |  | High | Access check |  | 8
13 | DaaS | Azure SQL DB | New DB instance creation | Provision and configure new DB | ARE / DaaS |  | 🟢 Not Started | Post backup completion | 2025-11-14 |  | Medium | Backup |  | 5
14 | DaaS | Azure SQL DB | EDP YAML PR & merge | Implement YAML changes, raise PR, merge | DaaS |  | 🟡 Planned |  | 2025-11-16 |  | Low |  |  | 3
15 | DaaS | Azure SQL DB | Change request | Submit CR for deployment | DaaS |  | 🟢 Not Started |  | 2025-11-17 |  | Low |  |  | 2
16 | DaaS | Azure SQL DB | Benchmark EDP flow | Record deployment duration (backup→restore) | DaaS |  | 🟢 Not Started | Will help in future planning | 2025-11-18 |  | Low |  |  | 3
17 | Verification | Azure SQL DB | Post-restore DB sizing validation | Revalidate DB sizing post restore | DBA / ARE / DaaS |  | 🟡 Planned | Should match 99% | 2025-11-20 |  | Medium | Backup restore |  | 4
18 | Verification | Azure SQL DB | Validation confirmation | Confirm match of objects, data, size | ARE / DaaS |  | 🟡 Planned |  | 2025-11-21 |  | Medium | Sizing validation |  | 4
19 | ITTE | Azure SQL DB | Shake-down data validation | Compare schemas, tables, data integrity | ITTE |  | 🟡 Planned | Run validation scripts | 2025-11-22 |  | High | DB validation |  | 6
20 | ITTE | Azure SQL DB | Application deployment test | Deploy app and test new DB | ITTE |  | 🟡 Planned | Post-restore verification | 2025-11-23 |  | Medium | Data validation |  | 5
21 | ITTE | Azure SQL DB | Cutover validation confirmation | Confirm cutover readiness | ITTE |  | 🟡 Planned | Final go/no-go | 2025-11-24 |  | High | App test |  | 4
22 | Next Steps | Azure SQL DB | Post-cutover delta check | Confirm no delta after restore & validation | ARE / DaaS / ITTE |  | 🟢 Not Started | Ensure maintenance window covers backup–cutover duration | 2025-11-25 |  | High | Cutover validation |  | 4
10 | DaaS | Azure Synapse | Current DB sizing inventory | Size, object count, list of schemas/tables/views | DBA / ARE / DaaS |  | ✅ Done | Sizing report shared | 2025-11-03 | 2025-11-03 | Low |  |  | 6 | 6
10 | DaaS | ADLS | Current DB sizing inventory | Size, object count, list of schemas/tables/views | DBA / ARE / DaaS |  | ✅ Done | Sizing report shared | 2025-11-03 | 2025-11-03 | Low |  |  | 6 | 6
11 | DaaS | Azure Synapse | Bitbucket access check | Confirm write/merge access to repo | DaaS |  | 🔄 In Progress | Access pending for few users | 2025-11-09 |  | Medium |  | Follow up with Infra | 2
11 | DaaS | ADLS | Bitbucket access check | Confirm write/merge access to repo | DaaS |  | 🔄 In Progress | Access pending for few users | 2025-11-09 |  | Medium |  | Follow up with Infra | 2
12 | DaaS | Azure Synapse | Backup & restore (point-in-time) | Execute EDP flow to restore backup | ARE / DaaS |  | 🟡 Planned | Requires maintenance window | 2025-11-12 |  | High | Access check |  | 8
12 | DaaS | ADLS | Backup & restore (point-in-time) | Execute EDP flow to restore backup | ARE / DaaS |  | 🟡 Planned | Requires maintenance window | 2025-11-12 |  | High | Access check |  | 8
13 | DaaS | Azure Synapse | New DB instance creation | Provision and configure new DB | ARE / DaaS |  | 🟢 Not Started | Post backup completion | 2025-11-14 |  | Medium | Backup |  | 5
13 | DaaS | ADLS | New DB instance creation | Provision and configure new DB | ARE / DaaS |  | 🟢 Not Started | Post backup completion | 2025-11-14 |  | Medium | Backup |  | 5
14 | DaaS | Azure Synapse | EDP YAML PR & merge | Implement YAML changes, raise PR, merge | DaaS |  | 🟡 Planned |  | 2025-11-16 |  | Low |  |  | 3
14 | DaaS | ADLS | EDP YAML PR & merge | Implement YAML changes, raise PR, merge | DaaS |  | 🟡 Planned |  | 2025-11-16 |  | Low |  |  | 3
15 | DaaS | Azure Synapse | Change request | Submit CR for deployment | DaaS |  | 🟢 Not Started |  | 2025-11-17 |  | Low |  |  | 2
15 | DaaS | ADLS | Change request | Submit CR for deployment | DaaS |  | 🟢 Not Started |  | 2025-11-17 |  | Low |  |  | 2
16 | DaaS | Azure Synapse | Benchmark EDP flow | Record deployment duration (backup→restore) | DaaS |  | 🟢 Not Started | Will help in future planning | 2025-11-18 |  | Low |  |  | 3
16 | DaaS | ADLS | Benchmark EDP flow | Record deployment duration (backup→restore) | DaaS |  | 🟢 Not Started | Will help in future planning | 2025-11-18 |  | Low |  |  | 3
19 | ITTE | Azure Synapse | Shake-down data validation | Compare schemas, tables, data integrity | ITTE |  | 🟡 Planned | Run validation scripts | 2025-11-22 |  | High | DB validation |  | 6
19 | ITTE | ADLS | Shake-down data validation | Compare schemas, tables, data integrity | ITTE |  | 🟡 Planned | Run validation scripts | 2025-11-22 |  | High | DB validation |  | 6
20 | ITTE | Azure Synapse | Application deployment test | Deploy app and test new DB | ITTE |  | 🟡 Planned | Post-restore verification | 2025-11-23 |  | Medium | Data validation |  | 5
20 | ITTE | ADLS | Application deployment test | Deploy app and test new DB | ITTE |  | 🟡 Planned | Post-restore verification | 2025-11-23 |  | Medium | Data validation |  | 5
21 | ITTE | Azure Synapse | Cutover validation confirmation | Confirm cutover readiness | ITTE |  | 🟡 Planned | Final go/no-go | 2025-11-24 |  | High | App test |  | 4
21 | ITTE | ADLS | Cutover validation confirmation | Confirm cutover readiness | ITTE |  | 🟡 Planned | Final go/no-go | 2025-11-24 |  | High | App test |  | 4

## Progress Heatmap
Team | Azure SQL DB | Azure Synapse | ADLS | Total Tasks | % Complete | Health
Infra | 100% | Shared Infra | Shared Infra | 9 | 100% | 🟢
DaaS | 35% | 30% | 25% | 21 | 30% | 🟡
ITTE | 0% | 0% | 0% | 9 | 0% | 🔴
Overall | - | - | - | 39 | 25% | 🟡

## Milestone Timeline
Milestone | Service | Start Date | End Date | Owner | Status | Comments
Subscription Setup | Azure SQL DB | 2025-11-01 | 2025-11-08 | Infra | ✅ Done | Access completed
Backup & Restore | Azure SQL DB | 2025-11-09 | 2025-11-12 | DaaS | 🟡 Planned | Pending window
Validation & Cutover | Azure SQL DB | 2025-11-20 | 2025-11-24 | ITTE | 🟡 Planned | Validation planned
Synapse EDP Flow | Azure Synapse | 2025-11-13 | 2025-11-18 | DaaS | 🟡 Planned | Follow SQL flow
ADLS Migration Tool Decision | ADLS | 2025-11-10 | 2025-11-11 | DaaS / Deloitte | 🔄 In Progress | Method selection pending

## Risk & Issue Log
Risk ID | Description | Impact | Probability | Severity | Owner | Mitigation Plan | Escalation Required (Y/N) | Status | Target Date | Last Updated
R1 | Access approval delays from Cloud Gov | High | Medium | High | Masood | Escalate to Infra lead for expedited review | Y | 🔄 Open | 2025-11-09 | 2025-11-09
R2 | NSG/Firewall rules pending before EDP flow | High | Medium | High | ARE | Submit network change request early | Y | 🟡 Planned | 2025-11-12 | 2025-11-09
R3 | Bitbucket repo merge rights not granted | Medium | Medium | Medium | DaaS | Follow up with Infra / DaaS | N | 🔄 In Progress | 2025-11-09 | 2025-11-09
R4 | DB restore duration exceeds maintenance window | High | Low | High | DaaS / ARE | Extend window + run benchmark test | Y | 🟡 Planned | 2025-11-18 | 2025-11-09
R5 | Post-cutover delta data miss risk | Critical | Low | High | ITTE / DaaS / ARE | Freeze writes during cutover | Y | 🟢 Not Started | 2025-11-25 | 2025-11-09

## Action Items and Decisions
Action ID | Description | Owner | Due Date | Status | Decision / Update
A1 | Confirm ADLS tool (AzCopy vs. ADF) | Deloitte / DaaS | 2025-11-11 | 🔄 In Progress | Pending decision
A2 | Approve extended maintenance window | AVP / ARE | 2025-11-12 | 🟡 Planned | Approval pending
A3 | Validate EDP flow for Synapse YAML | DaaS | 2025-11-14 | 🟢 Not Started | Post SQL run